## spltrack
VELAN METROLOGY - TOTAL ORDER PRODUCTION STATUS
SNO | PO NO | PO RECD DATE | CUSTOMER |  | Product Name | QTY | STATUS 1 | STATUS 2 | INHOUSE/ VENDOR | OP | TIMESTAMP
Customer Name
1 | AGIPLPO2017 | 2026-02-12 | LUCAS TVS |  | BASE PLATE | 1 NO |  | RM AVAILABLE, MOVE TO RK FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-28 10:18
[5 empty] | VEE BLOCK -1 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:22
| PROCESS WISE SHEET |  |  |  | VEE BLOCK -2 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:22
| INSPECTION DRAWING |  |  |  | RAIL PLATE | 2 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-21 15:42
| MATERIAL REQUISTION |  |  |  | T PLATE | 2 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-21 18:03
[5 empty] | L PLATE- 1 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:25
[5 empty] | L PLATE- 2 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:25
| MAY 5TH |  |  |  | JIG FEET | 4 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:12
[5 empty] | ANVIL | 2 NOS |  | PRETOOLING COMPLETED, WAITING FOR HT | INHOUSE | HTI | 2026-04-11 17:37
[5 empty] | PIN STOPPER | 1 NO |  | PRETOOLING COMPLETED, WAITING FOR HT | INHOUSE | HTI | 2026-04-11 17:38
[5 empty] | STOPPER-1 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:23
[5 empty] | RETAINER PIN | 4 NOS |  | PRETOOLING COMPLETED, WAITING FOR HT | INHOUSE | HTI | 2026-04-11 17:35
[5 empty] | ROLLER | 4 NOS |  | PRETOOLING COMPLETED, WAITING FOR HT | INHOUSE | HTI | 2026-04-11 17:36 | 6 NOS SENT,4 NOS-HT
[5 empty] | LOCKING PLATE | 2 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:12
[5 empty] | STOPPER-2 | 1 NO |  | PRETOOLING COMPLETED,MOVE TO SG TO RK | WITH VENDOR | SGV | 2026-04-16 18:23
[5 empty] | BUSH PIN | 1 NO |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 12:31
[5 empty] | KNURLING PIN | 1 NO |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:13 | 2 NOS SENT
[5 empty] | BUSH | 1 NO |  | PRETOOLING COMPLETED,HT COMPLETED,MOVE TO PRE ASS | INHOUSE | PRE ASS | 2026-04-20 12:32
[5 empty] | WASHER | 2 NOS |  | PRETOOLING COMPLETED,MOVE TO PRE ASS | INHOUSE | PRE ASS | 2026-04-11 17:40 | 4 NOS SENT
[5 empty] | HANDLE | 1 NO |  | PRETOOLING COMPLETED,MOVE TO PRE ASS | INHOUSE | PRE ASS | 2026-04-20 12:32
[5 empty] | BRASS BUSH | 2 NO |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-06 15:18
ACCESSORIES (BOUGHT OUT)
[5 empty] | SPRING | 1 NO |  | RM AVAILABLE IN STORES | INHOUSE | TO BE ORDER | 2026-04-18 11:54
[5 empty] | WING NUT | 2 NO |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-18 11:53
[5 empty] | ALLEN SCREW(M6*20) | 20 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-18 11:53
[5 empty] | ALLEN SCREW(M6*25) | 8 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-18 11:53
[5 empty] | ALLEN SCREW(M4*25) | 6 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-18 11:53
[5 empty] | M5 NUT | 4 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-18 11:53
[5 empty] | LM RAIL & GUIDE | 1 SET |  |  | INHOUSE | RM
[5 empty] | GRUB SCREW | 2 NOS |  | RM AVAILABLE IN STORES | INHOUSE | RM | 2026-04-02 15:16
2 | AGIPLPO2388 | 2026-04-04 | SA ENGG |  | BASE PLATE-BOTTOM | 1 NO |  | RM AVAILABLE, MOVE TO JMC FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-09 18:24
[5 empty] | BASE PLATE-TOP | 1 NO |  | RM AVAILABLE, MOVE TO JMC FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-09 18:24
| INSPECTION DRAWING |  |  |  | PROBE HOLDER | 4 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:13
| PROCESS WISE SHEET |  |  |  | LOCATOR | 1 NO |  | PRETOOLING,HT,SZ,BLK, COMPLETED,MOVE TO CG | INHOUSE | CG | 2026-04-18 11:57
| MATERIAL REQUISITION |  |  |  | JIG FEET | 4 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:13
[5 empty] | SHEET METAL | 4 NOS |  | PRETOOLING COMPLETED,MOVE TO PRE ASS | INHOUSE | PRE ASS | 2026-04-11 17:48
[5 empty] | ANVIL | 4 NOS |  | RM AVAILABLE, MOVE TO JV TOOLS FOR CG | WITH VENDOR | CGV | 2026-04-20 12:38
| MAY 5TH |  |  |  | BUSH | 4 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-20 12:39
[5 empty] | PROBE ACTUATOR | 4 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:14
[5 empty] | ANVIL HOLDER | 4 NOS |  | PRETOOLING COMPLETED,MOVE TO DRILL,TAP | INHOUSE | M1 | 2026-04-13 15:02
[5 empty] | MASTER | 1 NO |  | HT,SZ,BLK,SG,CG COMPLETED,MOVE TO CA | INHOUSE | CA | 2026-04-20 15:31
ACCESSORIES (BOUGHT OUT)
[5 empty] | ALLEN SCREW M6*15 | 22 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-17 11:16
[5 empty] | ALLEN SCREW M4*15 | 8 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-17 11:16
[5 empty] | ALLEN SCREW M3*10 | 32 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-17 11:16
[5 empty] | ALLEN SCREW M4*8 | 12 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-17 11:16
[5 empty] | ALLEN SCREW M4*25 | 4 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-17 11:16
[5 empty] | ELEMENT(SPRING STEEL) | 4 SETS |  | RM AVAILABLE,MOVE TO RK FOT PRETOOLING | WITH VENDOR | PTV | 2026-04-20 12:41
[5 empty] | WASHER | 60 NOS |  | RM AVAILABLE, MOVE TO RK FOR DRILLING,CUTTING | WITH VENDOR | PTV | 2026-04-09 18:24
3 | AGIPLPO2363 | 2026-03-30 | CIE |  | BASE PLATE | 1 NO |  | RM AVAILABLE, MOVE TO JMC FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-11 17:47
[5 empty] | TOP PLATE | 1 NO |  | RM AVAILABLE, MOVE TO JMC FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-11 17:47
| INSPECTION DRAWING |  |  |  | ANGLE PLATE | 2 NOS |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:14
| PROCESS WISE SHEET |  |  |  | MOVABLE DIAL BLOCK | 1 NO |  | RM AVAILABLE, MOVE TO JMC FOR PRETOOLING | WITH VENDOR | PTV | 2026-04-11 17:46
| MATERIAL REQUISITION |  |  |  | SQUARE PLATE | 1 NO |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:15
[5 empty] | DIAL SUPPORT BLOCK | 1 NO |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:15
[5 empty] | BUSH | 1 NO |  | LATHE COMPLETED,MOVE TO TAP,DRILL FOR RK | WITH VENDOR | SGV | 2026-04-16 18:22
| MAY 5TH |  |  |  | DIA 12 PIN | 1 NO |  | LATHE,HT,SZ,BLK COMPLETED,MOVE TO CG | INHOUSE | CG | 2026-04-21 11:37
[5 empty] | DIA 15 PIN | 1 NO |  | LATHE COMPLETED,MOVE TO TAP,DRILL FOR RK | WITH VENDOR | SGV | 2026-04-16 18:21
[5 empty] | PIN STOPPER | 1 NO |  | REWORK,MOVE TO PRETOOLING TO RK | WITH VENDOR | PTV | 2026-04-10 16:42
[5 empty] | BOTTOM PLATE | 1 NO |  | PRETOOLING,PRE ASS,BLK COMPLETED,MOVE TO ASS | INHOUSE | ASS | 2026-04-20 18:15
[5 empty] | SPRING | 1 NO |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-20 12:46
ACCESSORIES (BOUGHT OUT)
[5 empty] | ALLEN SCREW M6*30 | 12 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | ALLEN SCREW M6*25 | 4 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | ALLEN SCREW M6*20 | 4 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | CSK SCREW M4*15 | 2 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | CSK SCREW M4*10 | 6 NOS |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | ALLEN SCREW M4*18 | 1 NO |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-17 11:17
[5 empty] | BEARING 80/40/18 | 1 NO |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-20 12:57
[5 empty] | BALL KNOB M6 | 1 NO |  | RM AVAILABLE IN STORES | INHHOUSE | STOCK | 2026-04-20 12:57
[5 empty] | BALL PLUNGER | 3 NOS |  | RM AVAILABLE IN STORES | INHOUSE | STOCK | 2026-04-20 12:57
4 |  | REWORK - REPLCAMENT |  |  | POCLAIN | 1 NO |  | MILLING,DRILLING,HT COMPLETED,MOVE TO SG | INHOUSE | SG | 2026-04-13 16:49